## Work Orders
s.no. | Name of Contractor | Name of Work | Agreement No. | Date of Commencement | Stipulated date of Completion | Actual Date of Completion
1 | Abhinav Engineering and Suppliers | E/F work in Guru Govind singh samudayik bhavan in sayara panchayat samiti Udaipur | 104/2020-21 | 11/03/2021 | 10/03/2022 | 13/05/2022
2 | Abhinav Engineering and Suppliers | E/f in Vetnary Hospital Rishabdav Udaipur | 142/2014-15 | 20/03/2015 | 19/03/2016
3 | Arun Electricals | EF WORK IN APP OFFICE IN ADJ COURT NATHDWARA DISTT. UDAIPUR | 78/2023-24 | 18/10/2023 | 17/08/2024 | 19/06/2024
4 | Arun Electricals | E/f work in Record room at SDM office Kumbhalgarh distt Rajsamand | 22/2021-22 | 15/08/2021 | 14/05/2022 | 14/05/2022
5 | Arun Electricals | E/F work in Govt Primary school Building at Bhopa ki Bhagal Khamnore Dist Rajasamand | 63 of 2022-23 | 26/01/2023 | 25/11/2023 | 25/11/2023
6 | Arun Electricals | E/F work in Govt College building at Kumbhalgarh Rajsamand | 14/2019-20 | 15/08/2019 | 14/11/2020 | 23/02/2023
7 | Arun Electricals | E/F Work in Classroom at Kagmadarada Semal Distt Rajsamand | 72/2023-24 | 18/10/2023 | 17/10/2024 | 13/01/2025
8 | Arun Electricals | E/F in Lecture theatre Block RNT Medical College Udaipur | 133/2014-15 | 26/02/2015 | 25/08/2016 | 20/02/2020
9 | Arun Electricals | E/F work in 13 Additional Class room at Govt Sr Secondary School at Kothariya Dist Udaipur | 62 of 2022-23 | 26/01/2023 | 25/11/2023 | 25/11/2023
10 | Arun Electricals | Elect Rewiring and Various elect works in Circuit House Rajsamand | 95/2020-21 | 04/03/2021 | 03/09/2021 | 11/02/2022
11 | Arun Electricals | Electric Repair and Mtc work in Treasury Office Rajsamand | 56/2021-22 | 16/01/2022 | 15/07/2022 | 28/03/2022
12 | Arun Electricals | E/f work in Shikshak Awas Kotra | 107/2013-14 | 14/10/2013 | 13/04/2015 | 03/07/2019
13 | Arun Electricals | E/F Work in Classroom at Govt. Senior Secondary School Parsuniya (Tantol) Nathdwara Distt Rajsamand | 81/2023-24 | 17/12/2023 | 16/12/2024 | 16/12/2024
14 | Arun Electricals | E/F Work in Govt. School at Sinhad Nathdwara Distt. Rajsamand | 75/2023-24 | 18/10/2023 | 17/10/2024
15 | Arun Electricals | Electric repair and maintenance work of ward 4,5 and dharamshala T.B Hospital Badi Udaipur | 38/2023-24 | 29/09/2023 | 28/02/2024 | 20/07/2024
16 | Arun Electricals | Electric work in College Building at Lasadiya Dist Udaipur | 25 of 20221-22 | 27/08/2021 | 26/08/2023 | 20/08/2023
17 | Arun Electricals | E/F Work in I.T.I College Building at Kanore Distt. Udaipur | 84/2023-24 | 17/12/2023 | 16/06/2025
18 | Arun Electricals | E/F Work in New Govt I.T.I Building at Bhim District Rajsamand | 37/2023-24 | 24/09/2023 | 23/03/2025
19 | Arun Electricals | E/f work in Meeting Hall at SDM Office Kumbhalgarh | 20/2021-22 | 15/08/2021 | 14/08/2022 | 14/08/2022
20 | Arun Electricals | E/f work in govt girls College Building at Rajsamand | 61/2021-22 | 28/01/2022 | 27/10/2022 | 02/09/2022
21 | Arun Electricals | Elect renovation of TB Hospital Building RNT Medical College Udaipur | 23/2021-22 | 21/08/2021 | 20/08/2022 | 28/03/2022
22 | Arun Electricals | E/F Work in Classroom at Namana School Nathdwara Distt Rajsamand | 71/2023-24 | 18/10/2023 | 17/10/2024 | 17/02/2025
23 | Arun Electricals | Repair of 44 LSQ located in the New Complex Police Station Nathdwara District Rajsamand | 55/2021-22 | 16/01/2022 | 15/07/2022 | 21/03/2022
24 | Arun Electricals | EF work in executive engineer office building at Nathdwara Dist Rajasamand | 67 of 2023-24 | 18/10/2023 | 17/08/2024 | 10/01/2025
25 | Arun Electricals | Electrification work in Hostel For Govt Nursing college MB Hospitals at TB Hospital Campus Badi Udaipur | 13/2019-20 | 15/08/2019 | 14/08/2020 | 13/02/2021
26 | Arun Electricals | E/F work of Science Faculty in 5 Labs/Hall (physics chemistry Botany Zoology and Maths) with Verandah at Govt Collage Bhim Dist Rajasamand | 40 of 2021-22 | 18/10/2021 | 17/04/2023 | 17/04/2023
27 | Arun Electricals | Electric repair and renovation work of various department at MB Hospital Udaipur | 42/2021-22 | 13/11/2021 | 12/05/2022 | 20/07/2022
28 | Ashapura Electric | E/F Work in Police chowki javad district udaipur | 130/2015-16 | 14/02/2016 | 13/10/2016 | 08/06/2017
29 | AVON ELEVATORS | A.M.C. of Elevator in DJ Court in Court Campus, Udaipur | 51/2022-23 | 16/12/2022 | 15/05/2023 | 15/05/2023
30 | AVON ELEVATORS | Annual Maintenance contract of Passenger Elevator at DJ court Buiildings, Udaipur | 76 of 2021-22 | 24/03/2022 | 23/03/2023 | 29/09/2022
31 | Bajaj Electricals Ltd | Electric Lighting work in Block Level Rajiv Gandhi Model Khel Stadium at Tehsil Bhim Dist Rajsamand, FDPAID - 76173 | 91/2022-23 | 06/04/2023 | 06/10/2023 | 04/10/2023
32 | Balaji Refrigeation and Electricals | E/f Commercial Court on the V th Floor of New Court Complex at Distt Court Campus Udaipur | 92/2020-21 | 18/02/2021 | 17/08/2022
33 | Bhawani air systems | SITC of AC work in MCH Building Nathdwara Dist Rajsamand | 09/2023-24 | 19/08/2023 | 18/02/2024 | 07/03/2024
34 | Bitu Prabhat Electrical | Fire Detection and Fire Fighting work in Meeting Hall(Auditorium) at Khamnore Distt Rajsamand | 36 of 2023-24 | 23/09/2023 | 22/03/2024 | 27/07/2024
35 | GANPATI COMMUNICATION SERVICES | SITC of DG set and Substation work in Auditorium at Khammnore District Rajasamand | 49 of 2023-24 | 12/10/2023 | 11/04/2024 | 01/08/2024
36 | GANPATI COMMUNICATION SERVICES | EF work in Meeting Hall Auditorium at Khamnore dist Udaipur | 71 of 2022-23 | 04/02/2023 | 03/02/2024 | 01/08/2024
37 | Ganpati Engineering and Electricals | Remaining LAN Work in SR Hostel at RNT Medical College, Udaipur | 18/2022-23 | 25/09/2022 | 24/10/2022 | 23/10/2022
38 | Goyal Electricals | 11KV Substation Upgradation work in RNT Medical College Udaipur | 33 of 2022-23 | 20/11/2022 | 19/03/2023 | 18/03/2023
39 | Goyal Electricals | SITC of 250KVA Transformer work at TAD Commissionar Office Udaipur | 07/2023-24 | 20/08/2023 | 19/11/2023 | 09/02/2024
40 | Goyal Electricals | High Mast Lighting Work in RNT Medical College Udaipur | 19/2024-25 | 03/11/2024 | 02/01/2025 | 30/12/2024
41 | Goyal Electricals | SITC of Substation Work in Nursing Staff Quarters at RNT Medical College, Udaipur | 16/2022-23 | 09/09/2022 | 08/11/2022 | 08/11/2022
42 | Gupta Electricals | E/f in Govt College Building Railmagra Rajsamand | 43/2021-22 | 11/12/2021 | 10/06/2023 | 10/04/2023
43 | Gupta Electricals | E/f work of Science Faculty in 3 Classrooms and 2 Lecture theatre with verandah at Govt. College Bhim Dist. Rajsamand | 41/2021-22 | 08/10/2021 | 17/01/2023 | 10/04/2023
44 | Gupta Electricals | Electric renovation of RNT Medical College Udaipur | 27/2021-22 | 11/09/2021 | 10/09/2022 | 04/07/2022
45 | H M Engineers | Renovation and Upgradation of fire fighting system in MBGH Udaipur, FDPAID - 77098 | 99/ 2022-23 | 08/04/2023 | 07/11/2023 | 05/11/2023
46 | H M Engineers | Fire Fighting and Fire Detection System Work in Shri Sundar Singh Bhandari Hospital Ambamata Udaipur | 09/2024-25 | 31/08/2024 | 30/01/2025
47 | H M Engineers | Repair and Maintenance of fire fighting pump station at MBGH campus udaipur | 100/2023-24 | 24/03/2024 | 24/04/2024 | 01/04/2024
48 | H M Engineers | SITC of 250 KVA sub Station in Court Complex at session court campus Udaipur | 90/2017-18 | 12/02/2018 | 11/10/2018
49 | H M Engineers | Fire fighting work in nursing quarters 3rd type at RNT medical college Udaipur | 36/2022-23 | 27/11/2022 | 26/05/2023 | 24/04/2023
50 | H M Engineers | AMC of Fire Fighting system at DJ Court Campus Udaipur(2023-24) | 60/2023-24 | 12/10/2023 | 11/05/2024 | 11/05/2024
51 | H M Engineers | Upgradation Renovation of Fire Fighting System in MBGH campus Udaipur | 51/2023-24 | 12/10/2023 | 11/02/2024 | 06/04/2024
52 | H M Engineers | AMC of Fire Protection system at DJ Court Campus Udaipur | 82/2020-21 | 23/01/2021 | 22/01/2022 | 22/01/2022
53 | H M Engineers | AMC of Fire Fighting & Detection System at DJ Court Campus, Udaipur FY 2024-25 | 10/2024-25 | 31/08/2024 | 30/05/2025
54 | H M Engineers | AMC of fire fighting system in super speciality block at MBGH campus udaipur 2024-25 | 08/2024-25 | 31/08/2024 | 30/08/2025
55 | H M Engineers | AMC of Window & Spilt AC DJ Court Udaipur 2020-21 | 77/2020-21 | 22/01/2021 | 21/01/2022 | 21/01/2022
56 | K3 Construction Company | SITC of 500KVA DG Set with AMF Panel at NEW OPD Block at RNT Medical College Udaipur | 17 of 2022-23 | 24/09/2022 | 23/03/2023 | 20/03/2023
57 | Kartik Traders | SITC of ACs in Meeting Hall at SDM office at Kumbhalgarh Distt Rajsamand | 43/2022-23 | 16/01/2023 | 31/01/2023 | 30/01/2023
58 | Kartik Traders | E/f in Consumer court Circuit Bench court Campus Udaipur | 131/2016-17 | 18/03/2017 | 17/11/2017 | 10/03/2018
59 | KHATRI ELECTRIC SERVICE | Electrification work in Divisional and deputy director (rural) SI and GPF office Udaipur | 47/2021-22 | 06/01/2022 | 05/07/2023 | 28/08/2023
60 | KHATRI ELECTRIC SERVICE | E/f In Skill Development Canter RNT Medical Collage Udaipur | 29/2020-21 | 05/09/2020 | 04/03/2022 | 01/03/2022
61 | KHATRI ELECTRIC SERVICE | Electricfication work in Tahsil Building at Kherwada Dist. Udaipur | 45 of 2021-22 | 02/01/2022 | 30/06/2023 | 20/09/2023
62 | Krim Engineering | E/f in Ambedker Hostel Nathdwara Rajsamand | 117/2017-18 | 26/03/2018 | 27/04/2018 | 26/04/2018
63 | MANDORE FIRE SAFETY CENTRE | AMC of fire fighting system in MBGH campus udaipur fy 2024 & 2025 | 15/2024-25 | 05/10/2024 | 04/10/2025
64 | MANDORE FIRE SAFETY CENTRE | AMC and opration of fire fighting system at SSB building fire station at MBGH Udaipur | 94/2020-21 | 04/03/2021 | 03/03/2022 | 02/04/2022
65 | MANDORE FIRE SAFETY CENTRE | Annual Operation and Maintenance contract of fire Protection system at MBGH Campus Udaipur(2022-23) | 69 of 2022-23 | 26/01/2023 | 25/01/2024 | 25/01/2023
66 | MANDORE FIRE SAFETY CENTRE | Fire fighting work in satelite hospital at ambamata Udaipur | 45 of 2023-24 | 12/10/2023 | 11/02/2024 | 10/02/2024
67 | MANDORE FIRE SAFETY CENTRE | Fire Fighting Work in 20 nos Quarters For Nursing & Ministerial Staff at MGBH Campus, Udaipur | 78/2021-22 | 04/04/2022 | 03/07/2022 | 03/07/2022
68 | MANDORE FIRE SAFETY CENTRE | A.M.C. of Fire Fighting System in DJ Court Campus, Udaipur- | 41/22-23 | 15/12/2022 | 14/12/2023 | 15/05/2023
69 | MANDORE FIRE SAFETY CENTRE | AMC work of fire protection system in SSB at MBGH Udaipur (2022-23) | 40 / 2022-23 | 12/12/2022 | 11/12/2023 | 11/12/2023
70 | MANDORE FIRE SAFETY CENTRE | Fire Fighting Work in MCH Building Nathdawara Dist Rajsamand | 6/2023-24 | 08/08/2023 | 07/02/2024 | 10/03/2024
71 | MANDORE FIRE SAFETY CENTRE | Fire Fighting System for Central lab Janana Cottage and Exam Hall at MBGH campus Udaipur | 20/2024-25 | 03/11/2024 | 02/03/2025 | 15/02/2025
72 | Mechanical Services | SITC of Air conditioner work in meeting hall(Auditorium) at khamnore Distt.-Rajsamand | 57/2023-24 | 12/10/2023 | 11/04/2024 | 04/07/2024
73 | Metro International | AMC of 3 nos Passenger Elevator at DJ court campus Udaipur 2023-24 | 58/2023-24 | 12/10/2023 | 11/05/2024 | 11/05/2024
74 | Metro International | AMC of 3 Nos Passenger Elevator at DJ Court Campus Udaipur(FY 2024-25) | 03/2024-25 | 18/08/2024 | 17/05/2025 | 17/05/2025
75 | Metro International | AMC of Passenger Elevator at DJ Court Campus Udaipur 2020-21 | 53/2020-21 | 24/10/2020 | 23/10/2021 | 23/04/2022
76 | Metro International | CAMC of 3 nos Passenger Elevator in DJ Court Campus Udaipur | 67/2018-19 | 23/01/2019 | 22/01/2020 | 22/01/2020
77 | Metro International | AMC of 3 No Elevator at DJ Court Udaipur | 60/2019-20 | 14/02/2020 | 13/02/2021 | 13/02/2021
78 | Mitul Enterprises | Electric Repair and Maintenance work in Rajnagar Police Thana Building Dist Rajsamand | 69/2023-24 | 18/10/2023 | 17/03/2024 | 13/03/2024
79 | Mitul Enterprises | Supply and Providing wireman for electric maintenance in Various Govt Residence Building at Distt. Headquarters Udaipur | 29/2022-23 | 13/10/2022 | 12/10/2023 | 28/03/2023
80 | Mitul Enterprises | Supply of Electricians for general Electric maintenance in RNT Medical College Udaipur | 42/2022-23 | 12/12/2022 | 11/12/2023 | 29/12/2023
81 | Mitul Enterprises | Electricfication work at APO office at Sarada Dist Udaipur | 25/2023-24 | 10/09/2023 | 09/09/2024
82 | Mitul Enterprises | Electric Repair Work in Govt. Residential IIIrd and IVth Building Udaipur | 33/2024-25 | 22/11/2024 | 21/05/2025 | 21/05/2025
83 | Mitul Enterprises | E/f work in 5 nos toilet in Jail building Udaipur | 46/2022-23 | 12/12/2022 | 11/03/2023 | 10/03/2023
84 | Mitul Enterprises | Repairing of ceiling fan in govt residential building at udaipur | 17/2023-24 | 25/08/2023 | 24/08/2024 | 24/08/2024
85 | Mitul Enterprises | Supply of Electricians for General Maintenance in Trauma Block & near by Building Udaipur Fy 2025-26 | 62/2024-25 | 01/02/2025 | 31/01/2026
86 | Mitul Enterprises | Elect Repair and Mtc work in SP Office Rajsamand 2021-22 | 52/2021-22 | 15/01/2022 | 14/05/2022 | 30/03/2022
87 | Mitul Enterprises | Electrical Repair and Maintenance of Ceiling Fans, Coolers, Motors etc at various Govt Non Residential Building,Udaipur. | 74/2021-22 | 20/03/2022 | 19/09/2022 | 19/09/2022
88 | Mitul Enterprises | Electric repair and Maintenance work of Non Residential Govt. Building at Udaipur | 30/2024-25 | 22/11/2024 | 21/05/2025
89 | Mitul Enterprises | Electric repair and maintenance work in CJM residence at Rajsamand | 76 of 2022-23 | 19/02/2023 | 05/04/2023 | 26/03/2023
90 | Mitul Enterprises | Electric Repair and Maintenance of Ceiling Fan & Motor work in Non residential Building | 21/2023-24 | 10/09/2023 | 09/09/2024 | 09/09/2024
91 | Mitul Enterprises | Electric Repair and Maintenance of Girls Hostel Meera Girls College Udaipur | 69/2024-25 | 15/02/2025 | 14/08/2025
92 | Mitul Enterprises | providing of labour for electric repair/maintenance work in residential building Udaipur, FDPAID - 85565 | 18 of 2023-24 | 25/08/2023 | 24/02/2024 | 24/02/2024
93 | Mitul Enterprises | Electric repair maintenance work in non residential building at Udaipur | 23 of 2023-24 | 10/09/2023 | 09/09/2024 | 09/09/2024
94 | Mitul Enterprises | Repairing of Electric motors in Judicial Qtr at Udaipur | 51/2021-22 | 15/01/2022 | 30/01/2022 | 28/01/2022
95 | Mitul Enterprises | Electrification work in Govind Guru Samudayik Bhawan in Kherwada Panchayat Samiti, District- Udaipur | 33/2021-22 | 12/09/2021 | 11/09/2022 | 01/09/2022
96 | Mitul Enterprises | Electrical Repair and Maintenance of Ceiling Fans, Coolers, Motors etc at various Govt Residential Building,Udaipur. | 73/2021-22 | 20/03/2022 | 19/09/2022 | 19/09/2022
97 | Mitul Enterprises | SITC of transformer & Other Electrical work in New Building of Sale Tax Deptt. at Udaipur | 01/2022-23 | 24/05/2022 | 23/09/2022 | 22/09/2022
98 | Mitul Enterprises | Electric Repair and Maintenance Work at Lower Subordinate Quarter Building 12th Battalion RAC Debari Udaipur | 73/2024-25 | 15/02/2025 | 30/03/2025 | 21/03/2025
99 | Mitul Enterprises | Electric Repair and Maintenance Work in Excise Department, udaipur | 83/2024-25 | 01/03/2025 | 31/03/2025 | 22/03/2025
100 | Mitul Enterprises | Electric repair work in Rural treasury at collectorate office udaipur | 68/2022-23 | 26/01/2023 | 25/02/2023 | 25/02/2023
101 | Mitul Enterprises | Electric Repair and Maintenance work in III & IV Type Government residential quarter at udaipur | 22/2023-24 | 10/09/2023 | 09/09/2024 | 09/09/2024
102 | Mitul Enterprises | Electric repair and motor work in Saheliyon ki Bari, Udaipur | 49/2022-23 | 12/12/2022 | 11/01/2023 | 11/01/2023
103 | Mitul Enterprises | Electric Repair and Maintenance work in ADR Building of DLSA Rajsamand | 76/2023-24 | 18/10/2023 | 17/01/2024 | 16/01/2024
104 | Mitul Enterprises | Electric work in Collector Office at Rajsamand | 15/2022-23 | 07/08/2022 | 06/09/2022 | 18/08/2022
105 | Mitul Enterprises | Electric repair work and various electric for OSD office Salumber | 39/2023-24 | 12/10/2023 | 11/10/2024 | 28/02/2024
106 | Mitul Enterprises | Electric Repair Work and Maintenance work at Jyoti Bhawan, Udaipur | 50/2024-25 | 21/01/2025 | 20/03/2025 | 17/03/2025
107 | Mitul Enterprises | Electric Repair and Maintenance Work in CJ & JM Court Building Kotra Distt. Udaipur | 88/2024-25 | 01/03/2025 | 30/03/2025 | 22/03/2025
108 | Mitul Enterprises | Electric Repair/Renovation Work of Hostel Facility in HCM RIPA Udaipur | 47/2024-25 | 18/01/2025 | 17/04/2025 | 27/03/2025
109 | Mitul Enterprises | Electric repair work of APFC panel in saheliyon ki bari, udaipur | 24 / 2023-24 | 10/09/2023 | 09/10/2023 | 15/09/2023
110 | Mitul Enterprises | Supply and Providing wireman for electric maintenance in Various Govt. Non Residence Buildings at Distt. Headquarters Udaipur | 30/2022-23 | 13/10/2022 | 12/10/2023 | 28/07/2023
111 | Mitul Enterprises | EM work in JM residence Rajsamand | 74 of 2022-23 | 19/02/2023 | 05/04/2023 | 26/03/2023
112 | Mitul Enterprises | Remaining electric work for construction of Ladies Hostel at Shikshak Aavas Building at Kotra, District-Udaipur | 53/2021-22 | 16/01/2022 | 15/11/2022 | 07/10/2022
113 | Mitul Enterprises | Elect. rep. work in Residential Qtr Udaipur | 78 of 2022-23 | 19/02/2023 | 18/03/2023 | 09/03/2023
114 | Mitul Enterprises | Outdoor Lighting Repair/Recalling work at Super Speciality Hospital Udaipur | 43/2023-24 | 12/10/2023 | 11/12/2023 | 01/12/2023
115 | Mitul Enterprises | Electric repair and Maintenance work in various residential quarter at MB Hospital campus Udaipur | 30/2023-24 | 10/09/2023 | 09/03/2024 | 17/05/2024
116 | Mitul Enterprises | S/F Conduit pipe in Dy.Director (Rural) SI & GPF Office at Udaipur | 50/2021-22 | 15/01/2022 | 30/01/2022 | 28/01/2022
117 | Mitul Enterprises | Electrification work in Maharana Acharya Sanskrit College at Udaipur | 12/2022-23 | 18/07/2022 | 17/07/2023
118 | Mitul Enterprises | Electric renovation of Junior boys Hostel building at RNT Medical College Udaipur | 38/2021-22 | 05/10/2021 | 04/04/2022 | 04/04/2022
119 | Mitul Enterprises | Repair and renovation work in Police Qtr at Udaipur | 47/2022-23 | 12/12/2022 | 11/01/2023 | 10/01/2023
120 | Mitul Enterprises | Electric work for development of Covid Center for Jananna at Second Floor of Cottage Building at M.B. Hospital Udaipur | 37/2021-22 | 05/10/2021 | 04/04/2022 | 04/04/2022
121 | Mitul Enterprises | Electric Repair/ Maintenance work in I&II type Residential Quarters at Udaipur | 55 of 2023-24 | 12/10/2023 | 11/10/2024 | 11/10/2024
122 | Mitul Enterprises | Electric repair work in Non Residential GAD Building Udaipur | 90/2022-23 | 24/03/2023 | 30/03/2023 | 28/03/2023
123 | Mitul Enterprises | Electrification work at APO Office at Sarada Dist Udaipur | 25 of 2023-24 | 10/09/2023 | 09/09/2024 | 10/05/2024
124 | Mitul Enterprises | Elect work in 100 beded girls Hostel of Minority Deptt Udaipur | 04/2023-24 | 05/08/2023 | 04/08/2024
125 | Mitul Enterprises | Electric repair work in Ist,IIIrd & IV th Type Quarters at Udaipur | 30/2021-22 | 11/09/2021 | 10/05/2022 | 06/05/2022
126 | Mitul Enterprises | E/F work in Costruction of SDO & Tehsil Office building Girwa Udaipur | 49/2021-22 | 15/01/2022 | 15/04/2023 | 02/04/2024
127 | Mitul Enterprises | Electric sub main work at satellite hospital ambamata Udaipur | 26/2024-25 | 17/11/2024 | 16/01/2025 | 10/01/2025
128 | Mitul Enterprises | Electric Repair and Maintenance work in Residence No J1/3, Judge Commercial Court, Udaipur | 75/2021-22 | 20/03/2022 | 19/04/2022 | 25/03/2022
129 | Mitul Enterprises | Repairing and renovation of 13 rooms of PWD Dak Bungalow (acquired by circuit house) | 13/2022-23 | 30/07/2022 | 29/11/2022 | 29/11/2022
130 | Mitul Enterprises | Electric repair work in Ist,IIIrd & IV th Type Quarters at Udaipur | 30/2021-22 | 11/09/2021 | 10/05/2022
131 | Mitul Enterprises | EF work in class room at Govt Sr secondary School at Kotdi (Bilota) District Rajasamand | 65 of 2023-24 | 18/10/2023 | 17/08/2024 | 07/01/2025
132 | Mitul Enterprises | Electric Repair and maintenance work in staff toilet at bar association building rajsamand | 79/2023-24 | 18/10/2023 | 17/01/2024 | 17/01/2024
133 | Mitul Enterprises | Electric Repair and Maintenance work in Administrative Building and Guest house at RNT medical College Campus Udaipur | 27/2023-24 | 10/09/2023 | 09/03/2024 | 15/05/2024
134 | Mitul Enterprises | PF and replacement of exisitng lights by LED Flood bulkhead light in Sahelion ki bari Udaipur | 86 of 2022-23 | 22/03/2023 | 21/05/2023 | 15/05/2023
135 | Mitul Enterprises | EF work in meeting hall at Govt. SR. SEC. SCHOOL AT Shishavi Distt-Rajsamand | 44/2023-24 | 12/10/2023 | 11/08/2024 | 11/08/2024
136 | Mitul Enterprises | P/f of light luminaire and Electric repair work in old PG hostel (Near Child Hospital) at RNT Medical college Udaipur | 8/2021-22 | 09/08/2021 | 08/10/2021 | 10/09/2021
137 | Mitul Enterprises | providing of man power for Electric Repair/Maintenance Work in Non Residential Building at Udaipur, FDPAID - 85557 | 16 /2023-24 | 25/08/2023 | 24/08/2024 | 31/08/2024
138 | Mitul Enterprises | PF and Replacement of existing lights by LED flood Bulkhead in Sahelion ki bari Udaipur | 86 of 2022-23 | 22/03/2023 | 21/05/2023
139 | Mitul Enterprises | Electric work at various places at MBGH, Udaipur | 32/2022-23 | 13/11/2022 | 12/05/2023 | 02/01/2023
140 | Mitul Enterprises | Elect Rep and Renovation of Hostel Room in RIPA Udaipur | 48 of 2022-23 | 12/12/2022 | 11/03/2023 | 10/03/2023
141 | Mitul Enterprises | Electric repair and maintenance work in various wards Department of Radiodiagosis kitchen at MB Hospital Udaipur | 29/2023-24 | 10/09/2023 | 09/03/2024 | 28/05/2024
142 | Mitul Enterprises | Electric repair and Maintenace work in RNT Medical College Udaipur | 28/2023-24 | 10/09/2023 | 09/03/2024 | 08/03/2024
143 | Mitul Enterprises | E/M work in ACJM Residence at Rajsamand | 75/2022-23 | 19/02/2023 | 05/04/2023 | 26/03/2023
144 | Mitul Enterprises | Electric Repair Work and Maintenance Work at Dak Bunglow Udaipur | 51/2024-25 | 21/01/2025 | 20/03/2025 | 24/02/2025
145 | Mitul Enterprises | Upgradation of CCTV Cameras work in EVM/VVPAT store at Faras Khana in Udaipur | 59 of 2022-23 | 16/01/2023 | 16/03/2023 | 25/03/2023
146 | Navyug Engineering | Remaining Fire fighting work in Commercial Court on the Vth Floor of New Court Complex at District Court Campus, Udaipur | 02/2022-23 | 05/06/2022 | 04/12/2022
147 | Neha Electric | Electric Repair and Maintenace work in DJ Court Complex at Rajsamand | 56/22-23 | 09/01/2023 | 09/04/2023 | 24/03/2023
148 | Neha Electric | E/F work in dev narayan boys 50 Bedded hostel at nathdwara District-Rajsamand | 08/2023-24 | 17/08/2023 | 17/05/2024 | 05/07/2024
149 | Neha Electric | E/F work in Meeting at Tehsil Deogarh Distt. Rajsamand | 59/2023-24 | 16/10/2023 | 15/08/2024 | 15/08/2024
150 | Neha Electric | Remaining E/F Work in Girls Common Room at shri Heera Lal Devpura Govt. College Amet Distt Rajsamand | 28/2024-25 | 15/11/2024 | 14/03/2025 | 04/02/2025
151 | Neha Electric | Remaining E/FWork in 4 Classroom at Shri Heera Lal Devpura Govt. College Amet Distt. Rajsamand | 27/2024-25 | 15/11/2024 | 14/03/2025 | 09/02/2025
152 | Neha Electric | Providing and Fixing of LED Light Fixtures in ADJ Court Complex at Nathdwara Dist Rajsamand | 55/22-23 | 09/01/2023 | 09/04/2023 | 24/02/2023
153 | Neha Electric | E/F Work in Sub Tehsil Building at Diwer Distt. Rajsamand | 39/2024-25 | 26/12/2024 | 25/12/2025 | 30/07/2025
154 | Neha Electric | Electric work in Circuit House at Rajsamand | 82/2022-23 | 13/03/2023 | 26/04/2023 | 27/03/2023
155 | Neha Electric | EF work in Govt Sr Secondary School at Sagrun Dist Udaipur | 70 of 2022-23 | 04/02/2023 | 03/12/2023 | 31/08/2023
156 | Neha Electric | E/F Work in One stop center (SAKHI) Building at Rajsamand | 102/2022-23 | 09/04/2023 | 08/10/2023 | 03/01/2024
157 | Neha Electric | EF work in Govt Girls Sr School Building at Kothariya Distt Rajsamand | 79 of 2022-23 | 02/03/2023 | 03/12/2023 | 03/12/2023
158 | Neha Electric | E/F Work in Tehsil Building at Khamnore District rajsamand | 27/2022-23 | 16/10/2022 | 15/09/2023 | 11/07/2024
159 | Neha Electric | E/F Work in 4 additional classroom in govt Sr sec school bhim distt rajsamand | 74/2023-24 | 18/10/2023 | 17/08/2024 | 17/08/2024
160 | Neha Electric | E/f work in Residence Quarter Tehsildar at Garbhor Distt Rajsamand | 15/2020-21 | 09/07/2020 | 08/05/2021 | 09/03/2021
161 | Neha Electric | Electrification work in Govt College Building at Khamnore Dist. Rajsamand | 38 of 2022-23 | 02/12/2022 | 01/03/2024 | 26/07/2024
162 | Neha Electric | E/F work in Staff quarters at Circuit house Rajsamand | 65 of 2022-23 | 26/01/2023 | 12/03/2023 | 12/03/2023
163 | Neha Electric | Remaining E/F Work in Meeting Hall at Heera Lal Devpura Govt. College Amet Distt. Rajsamand | 29/2024-25 | 15/11/2024 | 14/03/2025 | 11/02/2025
164 | Neha Electric | E/f work in Tehsildar Residence at Devgarh Distt Rajsamand | 65/2019-20 | 14/02/2020 | 13/11/2020 | 13/11/2020
165 | Neha Electric | E/f in Govt. Nursing Hostel No 2 at MBGH Badi Campus Udaipur | 6/2020-21 | 19/06/2020 | 18/12/2021 | 21/07/2022
166 | Neha Electric | E/f work in Geography Lab at SRK College at Rajsamand | 12/2021-22 | 09/08/2021 | 08/06/2022 | 29/04/2022
167 | Neha Electric | Providing and Fixing of LED Light fixtures in DJ Court Complex at Rajsamand | 57/22-23 | 09/01/2023 | 09/04/2023 | 17/03/2023
168 | Neha Electric | EF work in resudence quarter of tehsildar at kumbhalgarh distt. Rajasmand | 37/2022-23 | 02/12/2022 | 01/06/2023 | 01/06/2023
169 | Neha Electric | E/F Work 4 Classroom at Shri Heera Lal Devpura College Amet District Rajsamand | 84/2022-23 | 13/03/2023 | 12/09/2023 | 03/12/2023
170 | Neha Electric | E/F Work in Library Building at SRK College Rajsamand | 40/2024-25 | 17/01/2025 | 16/07/2025 | 16/04/2025
171 | Neha Electric | Electric Repair and Maintenance Work at Record Room of DJ Court Complex at Rajsamand | 68/2024-25 | 15/02/2025 | 30/03/2025 | 22/03/2025
172 | Neha Electric | E/F work in Judicial residence at Dayal shah Rajsamand | 64 of 2022-23 | 26/01/2023 | 12/03/2023 | 10/03/2023
173 | Neha Electric | E/M work in SC ST Court at Rajsamand | 81/2022-23 | 13/03/2023 | 13/05/2023 | 26/03/2023
174 | Neha Electric | E/F Work in Development of Chawanda Mata Mandir at Railmagra Distt Rajsamand | 52/2023-24 | 12/10/2023 | 11/08/2024 | 30/12/2024
175 | Neha Electric | E/F Work in Classroom at Govt School Kunthwa Nathdwara Distt Rajsamand | 02/2025-26 | 12/04/2025 | 11/01/2026
176 | Neha Electric | E/F Work in Girl Common room at Shri Heera Lal Devpura College Amet Dist Rajsamand | 85/2022-23 | 13/03/2023 | 12/09/2023 | 08/12/2023
177 | Neha Electric | E/f work in Tehsildar Residence at Kunwariya Distt Rajsamand | 13/2021-22 | 09/08/2021 | 08/08/2022 | 12/12/2022
178 | Neha Electric | E/F Work in tehsildar residence quarters at khamnore distt rajsamand | 54/2023-24 | 12/10/2023 | 11/04/2024 | 01/10/2024
179 | Neha Electric | P&F of New LT Cable at DJ Court Complex at Rajsamand | 65/2024-25 | 15/02/2025 | 30/03/2025 | 06/03/2025
180 | Neha Electric | E/F Work in Meeting Hall at Heera lal Devpura Govt College Amet District Rajsamand | 83/2022-23 | 13/03/2023 | 12/09/2023 | 15/11/2023
181 | Omega Elevators | SITC of 15 Passengers / stretcher 4 stop Lift for Orthopedic, medical and Surgery wards in MB Hospital Campus, Udaipur | 4/2021-22 | 29/07/2021 | 28/01/2022 | 21/07/2022
182 | Omega Elevators | SITC of 10 Passengers 3 stop Lift at new Sales Tax Building Udaipur | 02/2021-22 | 29/07/2021 | 28/01/2022 | 22/03/2022
183 | Omega Elevators | SITC of 10 Passengers Elevator in Nursing Quarters (44 nos) at RNT Medical College, Udaipur | 68/2021-22 | 27/02/2022 | 26/12/2022 | 26/05/2023
184 | Omega Elevators | SITC of 10 Passengers Elevator in Nursing Quarters (20 nos) at RNT Medical College, Udaipur | 3/2021-22 | 29/07/2021 | 28/01/2022 | 13/06/2022
185 | ORBIS ELEVATOR CO LTD | SITC of 15 Passenger cum Stretcher Elevator in MBGH Main Porch at RNT Medical College Udaipur and SITC of 10 Passenger Elevator in Administrative Building at RNT Medical College Udaipur | 49/2024-25 | 24/01/2025 | 23/07/2025
186 | Powertech Engineers | Electric Repair and Maintenance Work in MACT Court at Rajsamand | 71/2024-25 | 15/02/2025 | 30/03/2025 | 24/03/2025
187 | Powertech Engineers | Electric Upgradation Work at Circuit House Rajsamand | 66/2024-25 | 15/02/2025 | 30/03/2025 | 25/03/2025
188 | Powertech Engineers | Various Electric Work in Non Residential Building for Rising Rajasthan Summit 2024 in District Rajsamand | 36/2024-25 | 22/11/2024 | 21/12/2024 | 07/12/2024
189 | Powertech Engineers | Various Electric Work in Residential Building for Rising Rajasthan Summit 2024 in district Rajsamand | 37/2024-25 | 22/11/2024 | 21/12/2024 | 07/12/2024
190 | Powertech Engineers | Various Electric Works in VWDC Centre at Court Complex Rajsamand | 89/2024-25 | 01/03/2025 | 30/04/2025 | 25/03/2025
191 | Powertech Engineers | Electric Repair and Maintenance Work in Govt Devnarayan Hostel Rajsamand | 42/2024-25 | 17/01/2025 | 16/04/2025 | 25/03/2025
192 | Powertech Engineers | Electric Repair and Maintenace work at POCSO Court Rajsamand | 67/2024-25 | 15/02/2025 | 30/03/2025 | 22/03/2025
193 | R S Enterprises | SITC of ACs in Tehsil Building at khamnore Distt Rajsamand | 13 of 2024-25 | 08/09/2024 | 07/11/2024 | 07/11/2024
194 | R S Enterprises | Electric Substation work at Nursing Hostel TB Hospital Campus Badi Udaipur | 77/2021-22 | 04/04/2022 | 03/07/2022 | 01/10/2022
195 | R S Enterprises | Remaining Electric Yard Work at TB Hospital badi Udaipur | 18/2024-25 | 25/10/2024 | 24/11/2024 | 18/11/2024
196 | R S Enterprises | SITC of ACs in Meeting Hall at Tehsil Building Deogarh Dist Rajsamand | 12 of 2024-25 | 08/09/2024 | 07/11/2024 | 07/11/2024
197 | R S Enterprises | Remaining electrification work in Govt college building at railmangra distt rajsamand | 98 year 2023-24 | 20/03/2024 | 21/07/2024 | 21/07/2024
198 | R S Enterprises | Upgradation reno of 11kv line lt line and substation on TB hospital badi udaipur | 35/2023-24 | 23/09/2023 | 22/04/2024 | 10/07/2024
199 | R S Enterprises | Line Shifting Work Gogunda Tula Machind Bada Bhanuja Gaon Gurha Jhalon ki Madar Sayon ka Kheda Sangath Rajsamand Road 0/0 to 14/500 Udaipur | 63/2024-25 | 08/02/2025 | 07/02/2026
200 | R S Enterprises | E/f work in Nursing Qtr (44 No) 3rd type at RNT Medical College Udaipur | 106/2020-21 | 15/03/2021 | 14/02/2023 | 22/03/2023
201 | RC POWER PROJECT LIMITED | SITC of Sound System Stage Drapery and stage lighting system in Auditorium at Khamnore Distt. Rajsamand | 66/2023-24 | 18/10/2023 | 17/10/2024
202 | Riddhi siddhi Enterprises | E/F Work in District Hospital Building at Nathdwara Distt. Rajsamand | 01/2024-25 | 30/06/2024 | 29/12/2025
203 | Sarvoday Electromart | Electric Repair and Maintenance Work of EMRS Community Hall at Kotra Distt. Udaipur | 25/2024-25 | 17/11/2024 | 16/05/2025 | 10/04/2025
204 | Satguru Electricals | E/f work in Ayurvedic Hospital Nathdwara Rajsamand | 89/2018-19 | 04/03/2019 | 03/09/2019 | 02/12/2019
205 | Seema Electricals | Electricfication of Residential Quarter for SDO at Kotra Udaipur | 93 of 2022-23 | 07/04/2023 | 06/06/2023 | 15/04/2023
206 | Seema Electricals | Electrical Wiring and Fixture Work in Newly Constructed VWDC Room at DJ Court Campus Udaipur | 02/2024-25 | 07/07/2024 | 06/11/2024 | 02/01/2025
207 | Seema Electricals | Electric repair and Maintenance of residential building at Dabok Police thana Udaipur | 58 of 2024-25 | 22/01/2025 | 21/03/2025 | 21/03/2025
208 | Seema Electricals | Electric Repair and Maintenance Work at Government College Level S.C. Girls Hostel Madhuban, Udaipur | 44/2024-25 | 17/01/2025 | 16/04/2025 | 10/02/2025
209 | Seema Electricals | AMC of A.C. in DJ Court Campus, Udaipur | 52/2022-23 | 16/12/2022 | 15/12/2023 | 15/05/2023
210 | Seema Electricals | Hire Charges of Various electric items for VIP Visit at Udaipur | 03/2022-23 | 11/05/2022 | 10/06/2022 | 16/05/2022
211 | Seema Electricals | Hire Charges of Tower type Air Conditioners system for VIP Visits at Udaipur | 01/2022-23 | 11/05/2022 | 10/06/2022 | 16/05/2022
212 | Seema Electricals | Electrical Maintenance work in Main building at MBGH Udaipur | 15/2023-24 | 25/08/2023 | 24/12/2023 | 06/11/2023
213 | Seema Electricals | Replacement of faulty change over at 500 KVA DG near pump house in electric work at MBGH udaipur | 14/2023-24 | 25/08/2023 | 24/10/2023 | 20/10/2023
214 | Seema Electricals | SITC of AC in Tehsil Building at Garbhor Distt Rajsamand | 71/2021-22 | 19/03/2022 | 18/04/2022 | 23/03/2022
215 | Seema Electricals | Electric Work in Circuit House at Rajsamand | 93/2023-24 | 13/03/2024 | 12/04/2024 | 20/03/2024
216 | Seema Electricals | Electrification work in Govind Guru Samudayik Bhawan in Rishabhdev Panchayat Samiti, District- Udaipur | 26/2021-22 | 11/09/2021 | 10/09/2022 | 05/09/2022
217 | Seema Electricals | SITC of CCTV Cameras work in EVM/VVPAT Warehouses at Rajsamand | 58/22-23 | 16/01/2023 | 16/03/2023 | 26/03/2023
218 | Seema Electricals | Electric repair and maintenance work of Dabok Police thana Udaipur | 57 of 2024-25 | 22/01/2025 | 21/03/2025 | 12/03/2025
219 | Seema Electricals | E/f in Canteen SIERT Building Udaipur | 99/2018-19 | 16/03/2019 | 15/09/2019 | 25/09/2019
220 | Seema Electricals | E F Work in Govt Sr Sec School Building At Dhaneriya Dist Rajsamand | 73/2022-23 | 12/02/2023 | 11/11/2023 | 11/11/2023
221 | Seema Electricals | AC work in Conference hall and Skill Section in Skil center at RNT Medical college Udaipur | 16 of 2024-25 | 25/10/2024 | 24/12/2024 | 18/12/2024
222 | Seema Electricals | AC work in Seminar hall on Second Floor of Psychiatry Department at MBGH Campus, Udaipur | 05/2022-23 | 18/06/2022 | 17/07/2022 | 17/07/2022
223 | Seema Electricals | E/F Work in Govt Sec Secondary School Building at Dhaneria Dist Rajsamand | 73 2022-23 | 12/02/2023 | 11/11/2023
224 | Seema Electricals | Electric repair Work in PWD campus at Udaipur | 11/2024-25 | 08/09/2024 | 07/11/2024 | 20/09/2024
225 | Seema Electricals | Annual Maintenance contract and Split AC at DJ Court campus, Udaipur | 70 of 2021-22 | 19/03/2022 | 18/03/2023 | 29/09/2022
226 | Seema Electricals | SITC of ACS at Govt College Building at khamnore district rajsamand | 56/2023-24 | 12/10/2023 | 11/04/2024 | 08/07/2024
227 | Seema Electricals | Electric Repair and Maintenance Work at Govt. Ambedkar Hostel Ambamata Goverdham Vilas Udaipur | 48/2024-25 | 18/01/2025 | 17/04/2025 | 01/03/2025
228 | Seema Electricals | Electrification work of new building for govt college at mavli district udaipur | 72/2022-2023 | 12/02/2023 | 11/01/2024 | 28/07/2024
229 | Seema Electricals | Electric Work in Sahelion ki Bari Udaipur | 59/2024-25 | 22/01/2025 | 21/03/2025 | 05/02/2025
230 | Seema Electricals | EF work in Classrooms at Upper Primary School at Joshiyo ki Madri Khamnore Dist Rajsamand | 35 of 2022-23 | 26/11/2022 | 25/09/2023 | 05/06/2023
231 | Seema Electricals | Elect mtc work in DJ Court Campus Udaipur 2020-21 | 49/2020-21 | 24/10/2020 | 23/10/2021 | 21/02/2021
232 | Seema Electricals | Electric Repair & Maintenance Work in Workshop, Nursery unit and Various Wards, at MBGH Campus Udaipur | 81/2024-25 | 01/03/2025 | 31/03/2025 | 23/03/2025
233 | Seema Electricals | Elect. Rep. work in Non Residential Building Udaipur | 89 of 2022-23 | 24/03/2023 | 30/03/2023 | 27/03/2023
234 | Seema Electricals | AMC Work of Window and Split ACs at DJ Court Campus, Udaipur | 14/2024-25 | 08/09/2024 | 07/09/2025
235 | Seema Electricals | Electrical work in Mortuary yard and Bal Chikitsalaya at MBGH Campus Udaipur | 52/2020-21 | 24/10/2020 | 23/02/2021 | 20/02/2021
236 | Seema Electricals | Electric repair and maintenace work of various wards old emergency center lab DDC and water proofing treatment | 68 of 2023-24 | 18/10/2023 | 17/04/2024 | 10/07/2024
237 | Seema Electricals | Electric Repair and Maintenance Work in Quarters No. 1/1 at Civil Lines Rajsamand | 27/2024-25 | 12/09/2024 | 11/10/2024 | 06/10/2024
238 | Seema Electricals | SITC of Air conditioning units in ADJ Court Kherwada, Dist.-Udaipur | 07/2022-23 | 18/06/2022 | 17/09/2022
239 | Seema Electricals | E/f work in Lab and ward at Satellite Hospital Hiran Magri Udaipur | 23/2020-21 | 15/08/2020 | 14/08/2021 | 28/08/2021
240 | Seema Electricals | Electrical Maintenance work in ward no. 5 and 6 and nearby building at Panadhay MBGH Udaipur | 92 of 2022-23 | 07/04/2023 | 06/06/2024 | 17/04/2023
241 | Seema Electricals | AMC of Window and split AC at DJ court campus Udaipur(2023-24) | 40/2023-24 | 12/10/2023 | 11/05/2024 | 11/05/2024
242 | Seema Electricals | Electric repair work in Various Non Residential Building Udaipur | 67/2022-23 | 26/01/2023 | 25/02/2023 | 20/02/2023
243 | Sheetal Refrigeration and Electricals | Remaining A.C. work in Sale Tax Office Udaipur | 14/2022-23 | 06/08/2022 | 05/10/2022 | 08/08/2022
244 | Shree Vinayak Electricals | Substation work in nursing Quarters 3rd Type at RNT Medical College Udaipur | 66 of 2022-23 | 26/01/2023 | 25/04/2023 | 25/04/2023
245 | SHREEJI ENTERPRISES UDAIPUR | Hire Charges of Temporary lighting work for VVIP in Rural area Udaipur | 90/2023-24 | 17/02/2024 | 16/02/2025 | 25/01/2025
246 | Shri Balaji Electrical | Electrical maintenace work in Govt Satelite hospital hiran magri Udaipur | 12/023-24 | 19/08/2023 | 18/10/2023 | 15/10/2023
247 | Shri Balaji Electrical | Transformer Shifting and Cabling Work in Intern Hostel at RNT Medical College Udaipur | 82/2024-25 | 01/03/2025 | 31/03/2025 | 28/03/2025
248 | Shri Balaji Electrical | Electric Repair & Maintenance Work at DJ Court Campus Udaipur | 38/2024-25 | 21/12/2024 | 20/04/2025 | 22/03/2025
249 | Shri Balaji Electrical | Supply of Electrician for General Maintenance in RNT medical college Udaipur | 86/2023-24 | 21/01/2024 | 20/01/2025 | 31/01/2025
250 | Shri Balaji Electrical | Electric Maintenance Work in Shree Sundersingh Bhandari rajkiya jila chikitsalay ambamata Udaipur | 13/2023-24 | 25/08/2023 | 24/10/2023 | 02/01/2024
251 | Shri Balaji Electrical | Electric Work on Facade Non Residential Building for Upcoming Rising Rajsathan, Summit 2024, Udaipur | 35/2024-25 | 22/11/2024 | 21/12/2024 | 07/12/2024
252 | Shri Balaji Electrical | Electric maintenance work in Lt shri khemraj katara rajkiye sattelite chiktsalay hiran magri udaipur | 11/2023-24 | 19/08/2023 | 18/10/2023 | 18/10/2023
253 | Shri Balaji Electrical | Providing and Fixing of Submersible Pump Motor in Circuit House Building at Udaipur | 07/2025-26 | 12/06/2025 | 11/07/2025 | 15/06/2025
254 | Shri Balaji Electrical | Electric repair and maintenance work in Administrative Building at Police thana Dhan Mandi Udaipur | 52 of 2024-25 | 21/01/2025 | 20/03/2025 | 20/03/2025
255 | Shri Balaji Electrical | Electric Work on Facade Residential Building for Upcoming Rising Rajasthan, Summit 2024 Udaipur | 31/2024-25 | 22/11/2024 | 21/12/2024 | 07/12/2024
256 | Shri Balaji Electrical | Electric repair and maintenace work im Janana OT cottage wards and Existing at MBGH Campus Udaipur | 26/2023-24 | 10/09/2023 | 09/03/2024 | 25/02/2024
257 | Shri Balaji Electricals | Electric work in yard near Autoclave Machine in Orthopedic building at MBGH Udaipur | 19/2023-24 | 10/09/2023 | 09/10/2023 | 20/09/2023
258 | Shri Govindam Enterprises | Reinstallation work of Dismantled Split Air Conditioners at Library Building at RNT Medical College Udaipur | 24/2022-23 | 16/10/2022 | 15/12/2022 | 01/12/2023
259 | Shri Govindam Enterprises | S and F of Air Conditioners in Information centre at Udaipur | 48/2021-22 | 06/01/2022 | 05/03/2022 | 05/03/2022
260 | Shri Govindam Enterprises | SITC of AC work in SDO Tahsil Office Building Girwa Udaipur | 94 of 2022-23 | 08/04/2023 | 07/04/2024 | 03/10/2023
261 | Shri Govindam Enterprises | SITC of ACs at Govt College Building at Railmagra Dist Rajsamand | 28 of 2022-23 | 22/10/2022 | 21/04/2023 | 21/04/2023
262 | Shri Govindam Enterprises | SITC of Air Conditioning for Development of Covid for Janana at Second floor of cottage Building at M.B. Hospital, Udaipur | 25/2022-23 | 16/10/2022 | 15/11/2022 | 14/11/2022
263 | Shri Sai Kripa Electrical Engineering Company | Electric repair and Maintenance works of Senior boys hostel at RNT Medical college Udaipur | 96 of 2022-23 | 08/04/2023 | 07/11/2023 | 01/11/2023
264 | Shri Sai Kripa Electrical Engineering Company | Electrical system Upgradation at Satelite Hospital Ambamata | 3/2023-24 | 29/07/2023 | 28/11/2023 | 25/01/2024
265 | Shri Sai Kripa Electrical Engineering Company | Electric Repair and Maintenance works of junior boys hostel at RNT Medical College Udaipur, FDPAID - 77013 | 98/2022-23 | 08/04/2023 | 07/11/2023 | 01/11/2023
266 | Shubham Electricals and Maintenance | AMC of 3 Nos Passenger Elevator in Court Complex at DJ Court Campus Udaipur (FY 2024-25) | 04/2024-25 | 18/08/2024 | 17/05/2025 | 17/05/2025
267 | Shubham Electricals and Maintenance | SITC of 1 Nos 6 Passenger Elevator in TAD Commissioner Office building Udaipur | 43/2018-19 | 27/12/2018 | 26/05/2019 | 26/09/2019
268 | Shubham Electricals and Maintenance | AMC of 3nosvpassenger elevator in new court complex at DJ court campus Udaipur | 50/2023-24 | 12/10/2023 | 11/05/2024 | 11/05/2024
269 | Shubham Electricals and Maintenance | A.M.C. of Elevator in new Court Complex at Court Campus, Udaipur | 50/2022-23 | 16/12/2022 | 15/05/2023 | 15/05/2023
270 | SK Electric Company | SITC of Fire Protection work in SDO & Tehsil Office Building Girwa Dist Udaipur | 95/2022-23 | 08/04/2023 | 07/02/2024 | 27/07/2023
271 | SK Electric Company | SITC of water tank for fire work in SDO and tehsil office building Girwa udaipur | 99/2023-24 | 24/03/2024 | 23/05/2024 | 22/05/2024
272 | Solution and Solution | LAN work in SR Hostel at RNT Medical College Udaipur | 21/2020-21 | 09/08/2020 | 08/02/2022 | 08/04/2021
273 | Som Electricals | E/f in ADJ Court Kherwara Distt Udaipur | 13/2020-21 | 27/06/2020 | 26/06/2021 | 01/09/2021
274 | Taniya Electricals | Electric repair and Maintenance work of Pratap Nagar Thana Quarters Udaipur | 56 of 2024-25 | 21/01/2025 | 20/03/2025 | 01/03/2025
275 | Taniya Electricals | Electrical Submain Work at Shri Khemraj Katara Satellite Hospital Hiran Magri Udaipur | 64/2024-25 | 08/02/2025 | 07/04/2025 | 07/04/2025
276 | Taniya Electricals | Electric Repair and Maintenance work of Girls Hostel and Audio Visual Lecture Room at Health Centre Vallabhnagar Udaipur | 46/2024-25 | 18/01/2025 | 17/04/2025 | 14/02/2025
277 | Techno Industries Pvt Ltd | SITC OF 15 PASSENGER CUM STRECHER ELEVATOR AT 15 BEDDED MCH BUILDING AT NATHDWARA DISTT-RAJSAMAND. | 62/2023-24 | 16/10/2023 | 15/02/2024 | 15/02/2024
278 | Techno Industries Pvt Ltd | SITC of 10 Passenger 3 stop lift for SDO and Tahsil Building of Girva Udaipur | 63/2023-24 | 16/10/2023 | 15/02/2024 | 10/06/2024
279 | Technoid Systems Solution | Remaining LAN Work in New OPD Block and Diagnostic Wing at RNT Medical College, Udaipur | 19/2022-23 | 26/09/2022 | 25/10/2022 | 23/10/2022
280 | Uma Ram and Sons | E/F work in 50 Baded MCH Building at Nathdwara district Udaipur | 23 of 2022-23 | 09/10/2022 | 08/02/2024 | 04/04/2024
281 | Vikas Enterprises | Supply and fixing of AMF panel for DG set at satellite Hospital Ambamata Udaipur | 34/2022-23 | 20/11/2022 | 19/02/2023 | 01/02/2023
282 | Vikas Enterprises | Electrification of extension of government polytechnic college at dakshin vistaar udaipur | 02/2023-24 | 15/06/2023 | 14/12/2023 | 10/12/2023
283 | Vikas Enterprises | Repair and upgradation works of TB Hospital at BADI Udaipur, FDPAID - 77014 | 01/2023-24 | 05/06/2023 | 04/12/2023 | 13/02/2024
284 | Vikas Enterprises | Electrification Work in Statistics Department in Bedla Udaipur | 09/2022-23 | 27/06/2022 | 26/12/2022 | 29/07/2022
285 | Vikas Enterprises | AMC of APFC panel installed at DJ court campus udaipur.(FY 23-24) | 41/2023-2024 | 12/10/2023 | 11/05/2024 | 11/05/2024
286 | Vikas Enterprises | Providing of Electrician for Govt Residential Vth Buildings Udaipur | 85/2024-25 | 01/03/2025 | 28/02/2026
287 | Vikas Enterprises | General Electric Repair work in Non Residential Building at Udaipur0 | 53/2023-24 | 12/10/2023 | 11/10/2024 | 11/10/2024
288 | Vikas Enterprises | Electric repair work in Govt. Residential Ist and llnd Building Udaipur (2024-25 Qtr-3) | 86/2024-25 | 01/03/2025 | 30/05/2025 | 30/05/2025
289 | Vikas Enterprises | Remaining E/F Work in construction of Divisional and Dy director(rural) SI and GPF at Udaipur | 97/2023-24 | 16/03/2024 | 15/06/2024 | 13/06/2024
290 | Vikas Enterprises | Annual Contract for Maintenance of APFC Panels installed DJ Court Campus, Udaipur | 69 of 2021-22 | 27/02/2022 | 26/12/2023 | 29/09/2022
291 | Vikas Enterprises | A.M.C. of APFC System in DJ Court Campus, Udaipur | 53/2022-23 | 16/12/2022 | 15/12/2023 | 15/05/2023
292 | Vikas Enterprises | Electric repair Work in Govt. Residential lllrd and IVth Building Udaipur (2024-25-Qtr-3) | 87/2024-25 | 01/03/2025 | 30/05/2025 | 30/05/2025
293 | Vikas Enterprises | Supply of Electricians for general Electric maintenance in MBGH Hospital Udaipur | 45/2022-23 | 12/12/2022 | 11/12/2023 | 29/12/2023
294 | Vikas Enterprises | Electricwork for Workshop building at RNT Medical College Udaipur | 57 of 2021-22 | 17/01/2022 | 16/01/2023 | 16/01/2023
295 | Vikas Enterprises | Electrification(Repair and Upgradation) work in Rajkiya Sampreshan avam Kishore Grah Building Udaipur | 11/2022-23 | 27/06/2022 | 26/12/2022 | 05/12/2022
296 | Vikas Enterprises | Electric Repair and Maintenance Work of Govt . Ambedkar Hostel at Gogla, Udaipur | 54/2024-25 | 21/01/2025 | 20/03/2025 | 20/02/2025
297 | Vikas Enterprises | E/F Work in Centeen at Polytechnic College at Rajsamand | 77/2023-24 | 18/10/2023 | 17/08/2024 | 17/08/2024
298 | Vikas Enterprises | Elect Renovation of senior Boys Hostel Building at RNT Medical College Udaipur | 36/2021-22 | 05/10/2021 | 04/04/2022 | 04/04/2022
299 | Vikas Enterprises | Electric Repair and maintenance work in CourtBuilding at Nathdwara Distt Rajasamand | 70/2023-24 | 18/10/2023 | 17/03/2024 | 11/03/2024
300 | Vikas Enterprises | Supply of Electricians for General Maintenance in RNT Medical College Udaipur Fy 2025-26 | 61/2024-25 | 01/02/2025 | 31/01/2026
301 | Vikas Enterprises | E/f work in Classroom at Govt. Sr. Secondry School Kunthwa Khamnor Rajsamand | 20/2022-23 | 30/09/2022 | 29/07/2023 | 15/02/2023
302 | Vikas Enterprises | E/f in Guru Govind Samudaiyk Bhawan DAL Salumber | 37/2020-21 | 16/10/2020 | 15/10/2021 | 10/10/2021
303 | Vikas Enterprises | Electric renovation of Jr. and Sr Girls Hostel building at RNT Medical College Udaipur | 35/2021-22 | 05/10/2021 | 04/04/2022 | 03/04/2022
304 | Vikas Enterprises | Electric Connection work for Govt College Building at Railmagra Rajsamand | 39/2022-23 | 12/12/2022 | 11/01/2023 | 28/12/2023
305 | Vikas Enterprises | Supply of Electricians for Genral Maintenance in Main Building MBGH Hospital Udaipur | 88/2023-24 | 25/01/2024 | 24/01/2025 | 31/01/2025
306 | Vikas Enterprises | Electric Repair and Maintenance Work at Upper Subordinate Quarter Building 12th Battalion RAC Debari Udaipur | 72/2024-25 | 15/02/2025 | 30/03/2025 | 21/03/2025
307 | Vikas Enterprises | Electrical Wiring work in ADR Court at DJ Court Campus, Udaipur (Capital Head-) | 54/2022-23 | 01/01/2023 | 01/03/2023 | 01/03/2023
308 | Vikas Enterprises | Electrical Repairing work at Various Court of District headquarter Udaipur | 95/2023-24 | 16/03/2024 | 15/04/2024 | 20/03/2024
309 | Vikas Enterprises | Electric Repair Work in Govt. Residential Ist and IInd Building Udaipur | 24/2024-25 | 17/11/2024 | 16/07/2025 | 15/01/2025
310 | Vikas Enterprises | Electric Renovation & Maintenance of Dining Hall & Mess at HCM RIPA Udaipur | 102/2023-24 | 24/03/2024 | 23/09/2024 | 18/12/2025
311 | Vikas Enterprises | Repairing of 250KVA Transformer at DJ Court Udaipur | 4/2022-23 | 18/06/2022 | 17/07/2022 | 17/07/2022
312 | Vikas Enterprises | Electric repair and MTC work in Various type lllrd and IVth type resi. Qtr Udaipur | 120/2020-21 | 21/03/2021 | 20/04/2021 | 20/04/2021
313 | Vikas Enterprises | Electric Repair and Mtc in Electric Panel romm at Shri Sunder Singh Bhandari Hospital Chandpol Udaipur | 115/2020-21 | 21/03/2021 | 04/04/2021 | 01/04/2021
314 | Vikas Enterprises | Supply of Electrician for General Maintenance in Trauma Block & Near by Building Udaipur 2023-24 | 87/2023-24 | 25/01/2024 | 24/01/2025 | 31/01/2025
315 | Vikas Enterprises | Remaining Electrification work in Tehsil Building at Kherwada District Udaipur | 94/2023-24 | 16/03/2024 | 15/06/2024 | 01/06/2024
316 | Vikas Enterprises | Electric Repair Work in Govt. Residential Vth Type Building Udaipur | 21/2024-25 | 17/11/2024 | 16/07/2025 | 10/06/2025
317 | Vikas Enterprises | AMC of APFC Panel installed DJ Court Campus Udaipur 2020-21 | 45/2020-21 | 24/10/2020 | 23/10/2021 | 23/10/2021
318 | Vikas Enterprises | P/L of HT and LT cable in Public Health Lab at MB Hospital premises, Udaipur | 58/2021-22 | 17/01/2022 | 16/02/2022 | 16/02/2022
319 | Vikas Enterprises | Hiring of Labour for Electrical Mtc of Residential Building Udaipur | 99/2019-20 | 21/03/2020 | 20/03/2021 | 20/03/2021
320 | Vikas Enterprises | Hire Charges of DG and Flood Lights for VIP Visit at Udaipur | 02/2022-23 | 11/05/2022 | 10/06/2022 | 16/05/2022
321 | Vikas Enterprises | Repair & Maintenance work (LT Cable, electric works) at CJ & JM Court Kherwara, FDPAID - 76185 | 80/2022-23 | 07/03/2023 | 06/04/2023 | 30/03/2023
322 | Vikas Enterprises | EF work in class room at Govt sr Secondary School Khamnore Distt Rajsamand | 21 of 2022-23 | 30/09/2022 | 29/07/2023 | 29/07/2023
323 | Vikas Enterprises | Providing of Labour for Day to Day Electric Maintenance Work in Govt. Residential Building Udaipur (IIIrd type and IVth type Quarters 2024-25) | 23/2024-25 | 17/11/2024 | 16/05/2025 | 31/03/2025
324 | Vikas Enterprises | Electric repair work in govt residential udaipur | 88/2022-23 | 24/03/2023 | 30/03/2023 | 27/03/2023
325 | Vikas Enterprises | Electric repair and Maintenace work in trauma and blood bank at MBGH campus Udaipur | 31/2023-24 | 13/09/2023 | 12/01/2024 | 10/01/2024
326 | Vikas Enterprises | Earthing work and other repair work at excise building at udaipur | 101/2023-24 | 24/03/2024 | 23/06/2024 | 13/06/2024
327 | Vikas Enterprises | Electric Repair and Maintenance Work at Administrative Building 12th Battalion RAC Debari Udaipur | 79/2024-25 | 20/02/2025 | 05/04/2025 | 23/03/2025
328 | Vikas Enterprises | AMC Work of APFC Panel Installed at DJ Court Campus, Udaipur | 05/2024-25 | 31/08/2024 | 30/08/2025
329 | Vikas Enterprises | HTDP structure related work in Mines & Geology Deptt. Udaipur | 113/2020-21 | 21/03/2021 | 04/04/2021 | 12/03/2021
330 | Vikas Enterprises | Electrification of Seating and Prayer Hall (60X40) at Govt Se.Sec. School at Brahmano ka kherwada in Jhadol Distt. Udaipur | 100/2023-24 | 08/04/2023 | 07/07/2023 | 06/07/2023
331 | Vikas Enterprises | Electric Renovation Work in State Motor Garrage Building Udaipur | 70/2024-25 | 15/02/2025 | 14/04/2025 | 27/03/2025
332 | Vikas Enterprises | Supply of experienced wireman Electricians for day to day maintenance for MB hospital and its associates building Udaipur | 29/2021-22 | 11/09/2021 | 10/09/2022 | 10/09/2022
333 | Vikas Enterprises | Electrical maintenance and Upgradation of electric substation in MBGH Udaipur, FDPAID - 77098 | 101/2023-24 | 08/04/2023 | 07/07/2023 | 07/07/2023
334 | Vikas Enterprises | Supply of Electricians for General Maintenance in Main Building MBGH Hospital Udaipur Fy 2025-26 | 60/2024-25 | 01/02/2025 | 31/01/2026
335 | Vikas Enterprises | Providing of Labour for Day to Day Electric Maintenance Work in Govt. Non Residential Building Udaipur | 17/2024-25 | 25/10/2024 | 24/10/2025
336 | Vikas Enterprises | Additional Electrification of Extension of Govt Polytechnic College at Dakshin Vistaar Udaipur | 07/2024-25 | 31/08/2024 | 30/10/2024 | 30/10/2024
337 | Vikas Enterprises | Electric Repair and Maintenance Work at Gulab Barrack (100 Men) 12th Battalion RAC Debari Udaipur | 80/2024-25 | 20/02/2025 | 05/04/2025 | 20/03/2025
338 | Vikas Enterprises | Electric repair and Maintenance work of Administrative Building at Police thana Pratap Nagar Udaipur | 55 of 2024-25 | 21/01/2025 | 20/03/2025 | 10/03/2025
339 | Vikas Enterprises | Electri repair and maintenance work in Lecture theatre exam Building auditiorium old libary, badminton court at RNT Medical college Udaipur | 32/2023-24 | 13/09/2023 | 12/01/2024 | 12/01/2024
340 | Vikas Enterprises | Electric Repair and maintenance work of Cardiology and SSH Building at MB Hospital Campus Udaipur | 34 of 2024-25 | 13/09/2023 | 12/01/2024 | 24/04/2024
341 | Vikas Enterprises | Electric repair and maintenance work in various hostel (New Junior boys,SR hostel, Intern hostel Nursing Hostel ) at RNT Medical college Udaipur | 33/2023-24 | 13/09/2023 | 12/01/2024 | 10/03/2024
342 | Vikas Enterprises | Supply of Electricians for general Electric maintenance in Trauma Block & Near by Building Udaipur | 44/2022-23 | 12/12/2022 | 11/12/2023 | 29/12/2023
343 | Vikas Enterprises | Tender for the work Temporary lighting arrangement work during VIP visit in Udaipur | 3/2022-23 | 03/06/2022 | 02/06/2023 | 09/06/2022
344 | Vikas Enterprises | Electric Repair and Maintenance works at Cardiology Department, SSH , UG/PG girls hostel and GNM lecture hall at RNT Medical College Udaipur-, FDPAID - 77015 | 97/2022-23 | 08/04/2023 | 07/11/2023 | 27/10/2023
345 | Vimal Electricals | Providing of Labour for day to day Electric Manitenance Work in Govt. Residential Building at Udaipur | 92/2023-24 | 14/03/2024 | 13/11/2024 | 13/11/2024
346 | Vimal Electricals | Electric work in Science Lab at Vigyan samiti Ashok Nager Udaipur | 81/2020-21 | 23/01/2021 | 22/07/2021 | 22/07/2021
347 | Vimal Electricals | Elect rep. work in Non Residential Qtr Udaipur | 77 of 2022-23 | 19/02/2023 | 18/03/2023 | 18/03/2023
348 | Vimal Electricals | Electric repair work in Judicial quarters at District head quarter Udaipur | 96/2023-24 | 16/03/2024 | 15/04/2024 | 28/03/2024
349 | Vimal Electricals | S/f of Elect Material for Mtc of Various Govt Resi Building Udaipur | 19/2021-22 | 15/08/2021 | 14/06/2022 | 10/06/2022
350 | Vimal Electricals | Electric repair work of Government residential Quarter l/132(Judicial Magistrate Family Court no-1) at Pratap Nagar Distt Udaipur | 87 of 2022-23 | 24/03/2023 | 30/03/2023 | 26/03/2023
351 | Vimal Electricals | E/F Work in Center for Studies of Value at Chitrakoot Nagar Udaipur | 48/2023-24 | 12/10/2023 | 11/12/2023 | 01/12/2023
352 | Vimal Electricals | Electric Repair and Maintenance Work of OBC Hostel Biliya Udaipur | 45/2024-25 | 18/01/2025 | 17/04/2025 | 20/02/2025
353 | Yashaswini Enterprises | E/f work in Residence Qtr for SDO At Kotra Distt Udaipur | 56/2020/21 | 14/11/2020 | 13/11/2021 | 13/03/2021
354 | Yashaswini Enterprises | E/f work in Tehsil Building in Garbhor Distt Rajsamand | 122/2020-21 | 22/03/2021 | 21/06/2022 | 17/05/2022
355 | Yashaswini Enterprises | Elect work in 20 Nos Qtr for Nursing and Ministerial staff at MBGH Campus Udaipur | 07/2020-21 | 19/06/2020 | 18/12/2021 | 18/05/2022